## Product Backlog
Product Name: | Mav’s Animal Shelter Software (MASS) | [6 empty] | Complete Fields in Green!!!
Team ID:
| Team Member Name | [5 empty] | Initials | Student ID
Required | Kolade Favour Oluwadamilola | [5 empty] | KFO | 1001860786
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 22 |  |  |  | Total | Total number of features (in column H)
1 | 18 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 11 | 7 |  |  | 2 | Total features left at the end of Sprint #2
3 | 6 | 5 |  |  | 3 | ...and so on
4 | 3 | 3
5 | 0 | 3
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
ANIMAL | 1 | 1 |  | 5 | 1 | Finished in Sprint 1 | User | Track the name, gender, and age for all animals | Keep track of guests at our shelter | Need enum for Gender and abstract Animal class with constructor, getters, and toString. Validate that age is not negative else throw an exception.
DOG | 2 | 1 |  | 8 | 1 | Finished in Sprint 1 | Staff | Create a new dog (or any other family of animals) | Track pets seeking good homes | Need Dog class that extends Animal along with DogBreed enum (may be any animal family, not necessarily Dog).
LANIM | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Staff | Keep a list of animals | See what animals are available | Requires Shelter class with a shelter name and array list of animals. Need to be able to add an animal and access the available animals.
CAT | 4 | 1 |  | 5 | 1 | Finished in Sprint 1 | Staff | Create and list cats (or 2nd animal family) as well | Put 2nd pet type up for adoption | Very similar to 1st type of pets
MAINWIN | 5 | 2 |  | 3 | 2 | Finished in Sprint 2 | User | Display a main window with menu | Use the program more easily | Baseline Nim
TOOLBAR | 6 | 2 |  | 2 | 2 | Finished in Sprint 2 | User | Include a toolbar | Click buttons for actions | Baseline Nim; add 2 buttons for inserting the two animal families
ABOUT | 7 | 2 |  | 3 | 2 | Finished in Sprint 2 | User | Include an About dialog for toolbar icons (Help > About) | Avoid legal trouble | Baseline Nim; need icons for the two animal families; use YOUR name
EXIT | 8 | 2 |  | 2 | 2 | Finished in Sprint 2 | User | Exit the main program (File > Quit or x window control) | Quit reliably | Baseline Nim
DOGDIALOG | 9 | 2 |  | 13 | 2 | Finished in Sprint 2 | Staff | Use dialogs to create a new dog or 1st family (Animal > New) | Track pets seeking good homes | May be a series of JOptionPane dialogs or a single unified dialog
CATDIALOG | 10 | 2 |  | 8 | 2 | Finished in Sprint 2 | Staff | Use dialogs to create a new cat or 2nd family (Animal > New) | Track more pets seeking good homes | Similar to 1st
SHOWANIM | 11 | 2 |  | 5 | 2 | Finished in Sprint 2 | Staff | Display all animals in the main window (Animal > List Available) | See the beloved animals that are current guests of the shelter | Update after every Insert operation (Animal > List Available will be needed when clients are added in a later sprint). May be a label or similar widget in the data area of the main window
SAVE | 12 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | Requires Animal.save(bw), Dog.save, Cat.save, Shelter.save; Shelter.filename with getter and setter, and Mass.onSaveClick
LOAD | 13 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Load the data from a default file (File > Open) | Persist our data through the years | Requires Animal.Animal(br), Dog.Dog, Cat.Cat, Shelter.Shelter and Mass.onOpenClick; dialog and logic for handling “dirty” data
NEW | 14 | 3 |  | 5 | 3 | Finished in Sprint 3 | Director | Create a new shelter (File > New) | Open additional shelters as needed | Requires Mass.onNewShelterClick
SAVEF | 15 | 3 |  | 5 | 3 | Finished in Sprint 3 | Director | Save the data to a specified file (File > Save As) | Backup or baseline a new shelter | Requires Mass.onSaveAsClick, Shelter.setFilename; adding JFileChooser
LOADF | 16 | 3 |  | 3 | 3 | Finished in Sprint 3 | Director | Load the data from a specified file (File > Open) | Work with multiple shelters | Requires adding JFileChooser
GENERIC | 17 | 4 |  | 13 | 4 | In Work | Staff | Refactor Add (Animal) dialogs into generic class and add at least one additional family of animals | Quickly add additional animal families to our guest list | Requires generic class for unified dialog to create new animal guests
ITER | 18 | 5 |  | 5 |  |  |  | Refactor to use iterators to access animals from Shelter | Practice iterators (well?) | Replace numAnimals and getAnimal with getAnimalIterator; update all users of those methods
CLIENT | 19 | 4 |  | 8 | 4 | Finished in Sprint 4 | Staff | Create a new client (Client > New) | Track candidate adopters | Requires Mass.onCreateClient; 1 dialog; class Client; Shelter.addClient and fields
LCLIENT | 20 | 4 |  | 5 | 4 | Finished in Sprint 4 | Client | List clients (Client > List) | See which clients are available | Requires Shelter.numClients and client; and Mass.onClientsList
ADOPT | 21 | 5 |  | 13 |  |  | Client | Adopt an animal (Client > Adopt Animal) | Adopt an animal! | Requires Shelter.adopted HashMap<Animal, Client>, new dialog
LADOPT | 22 | 5 |  | 8 |  |  | Staff | List adopted animals (Client > List Adopted and Animal > List Adopted) | See which client adopted which animal | Requires 1 dialog to select the client and 1 dialog to select the animal; Mass.onListAdoptedClick
Bonus Features
NANIM |  | 4 | TBD | 5 |  | Finished in Sprint 4 | Client | Create new animals and / or clients during adoption | Simplify the adoption process | Add “New Client” button to the client selection dialog; Add “New Animal” button to the animal selection dialog; add logic to integrate smoothly
PHOTO |  | 4 | TBD | 8 |  |  | Client | See photo and information about an available animal | Decide if it’s right for my family | Requires existing animal selection dialog + 1 dialog derived from Animal > New with a Gtk::Image, Mainwin::on_view_animal_click.

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2022-02-22 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-01
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 9
Day 1 Left | 7 | 2
Day 2 Left | 3 | 4
Day 3 Left | 2 | 1
Day 4 Left | 2 | 0
Day 5 Left | 2 | 0
Day 6 Left | 2 | 0
Day 7 Left | 0 | 2
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | ANIMAL |  | create abstract class animal | Completed Day 1
2 | ANIMAL |  | create methods family, breed, toString | Completed Day 1
3 | DOG |  | create DogBreed enum | Completed Day 2
4 | DOG |  | override methods from abstract class | Completed Day 2
5 | CAT |  | create CatBreed enum | Completed Day 2
6 | CAT |  | override methods from abstract class | Completed Day 2
7 | ANIMAL |  | create Gender enum | Completed Day 3
8 | LANIM |  | create Shelter class | Completed Day 7
9 | LANIM |  | test Shelter class with Mass. Java | Completed Day 7
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2022-03-01 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-08
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 16
Day 1 Left | 16 | 0
Day 2 Left | 16 | 0
Day 3 Left | 13 | 3
Day 4 Left | 11 | 2
Day 5 Left | 6 | 5
Day 6 Left | 1 | 5
Day 7 Left | 0 | 1
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | MAINWIN |  | create main window | Completed Day 3
2 | MAINWIN |  | put menu options such as add new animal; dog or cat | Completed Day 3
3 | TOOLBAR |  | include toolbar to add dog, make icons or buttons for them | Completed Day 4
4 | TOOLBAR |  | include toolbar to add cat, make icons or buttons for them | Completed Day 4
5 | MAINWIN |  | put main window in Mass.java | Completed Day 3
6 | TOOLBAR |  | Let person be allowed to put in new animals | Completed Day 6
7 | TOOLBAR |  | Make sure buttons for adding new animals work | Completed Day 6
8 | ABOUT |  | include help > about in main window | Completed Day 5
9 | ABOUT |  | create about dialog that tells what the program does | Completed Day 6
10 | EXIT |  | allow user to leave the program through File > Quit | Completed Day 5
11 | SHOWANIM |  | Include list under animal in menubar | Completed Day 5
12 | SHOWANIM |  | allow user to see a list all the animlas they entered | Completed Day 7
13 | DOGDIALOG |  | create dialog that allows user to put in a new dog | Completed Day 5
14 | CATDIALOG |  | create dialog that allows user to put in a new cat | Completed Day 5
15 | DOGDIALOG |  | put in breed, name , age and gender of new dog | Completed Day 6
16 | CATDIALOG |  | put in breed, name , age and gender of new cat | Completed Day 6
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2022-03-08 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-03-15
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 21
Day 1 Left | 17 | 4
Day 2 Left | 13 | 4
Day 3 Left | 4 | 9
Day 4 Left | 4 | 0
Day 5 Left | 3 | 1
Day 6 Left | 3 | 0
Day 7 Left | 0 | 3
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | NEW |  | Create New shelter dialog | Completed Day 1
2 | SAVE |  | add file > save to menubar | Completed Day 2
3 | LOAD |  | add file > open to menubar | Completed Day 2
4 | SAVEF |  | add file > save as to menubar | Completed Day 2
5 | SAVE |  | put icon in toolbar | Completed Day 3
6 | SAVEF |  | put icon in toolbar | Completed Day 3
7 | LOAD |  | put icon in toolbar | Completed Day 3
8 | NEW |  | put icon in toolbar | Completed Day 2
9 | SAVE |  | create save function | Completed Day 5
10 | NEW |  | create new shelter lamda | Completed Day 1
11 | ANIMAL |  | read in data in Animal class | Completed Day 3
12 | CAT |  | read in data in Cat | Completed Day 3
13 | DOG |  | read in data in Dog | Completed Day 3
14 | ANIMAL |  | write data to file in Animal | Completed Day 3
15 | CAT |  | write data to file in Cat | Completed Day 3
16 | DOG |  | write data to file in Dog | Completed Day 3
17 | ANIMAL |  | add save method in Animal abstract class | Completed Day 1
18 | ANIMAL |  | add Animal constructor to abstract class | Completed Day 1
19 | SAVEF |  | tested save as with main window | Completed Day 7
20 | LOADF |  | tested open shelter with main window | Completed Day 7
21 | LOADF |  | tested file opening with main window | Completed Day 7
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2022-04-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 12
Day 1 Left | 12 | 0
Day 2 Left | 12 | 0
Day 3 Left | 8 | 4
Day 4 Left | 8 | 0
Day 5 Left | 7 | 1
Day 6 Left | 1 | 6
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CLIENT |  | Create client class in package shelter | Completed Day 3
2 | CLIENT |  | create dialog for new client | Completed Day 5
3 | NANIM |  | create new animal class; Rabbit | Completed Day 3
4 | NANIM |  | create dialog for rabbit in Mainwin.java | Completed Day 3
5 | NANIM |  | create buttons and add to the toolbar for rabbit | Completed Day 3
6 | GENERIC |  | create generic for animal types | In Work
7 | LCLIENT |  | list all clients in the adoption centre | Completed Day 6
8 | CAT |  | override create method for animals to use in generic | Completed Day 6
9 | DOG |  | override create method for animals to use in generic | Completed Day 6
10 | ANIMAL |  | write create method for animals to use in generic | Completed Day 6
11 | CLIENT |  | make button for client | Completed Day 6
12 | CAT |  | make button for other animal | Completed Day 6
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2022-04-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-04-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84